CTEC Development Program Advisory Committee

2011-12 Work Plan

| Annual Goal Area | Strategies | Timeline | Advisory Committee Member Participation |
| --- | --- | --- | --- |
| CURRICULUM Goal(s): |  |  |  |
| Design, create, validate and approve a viable web/applications development and/or web support program to be rolled out during the 2013 catalog cycle | - Advisory review of O*Net Department of labor summary information and other job information - Advisory review of web dev curricula, primarily those from other regional programs - Consideration of creation of DACUM or focus group if it is determined that more definition and data are needed | Spring-Fall 2011 for outcomes review. Spring 2012 for completion of program | Email-mediated Ad Hoc group of advisory to review and rank prior to Spring or Fall 2011 Advisory meeting |
| FACILITIES & EQUIPMENT Goal(s): |  |  |  |
| Identify and refine a server environment tailored for students to interact in that is equivalent to professional web development environment. | - Identify ideal server configuration for development instructional environment. And identify solutions for staging these: Clark servers, server space from outside vendors or cloud and virtual environments. | Fall 2011 | Email-mediated Ad Hoc group of advisory to review and develop prior to Fall Advisory meeting |
| Specify a laptop options for the serious development student and consider it as a requirement for program delivery. |  | Winter 2012 | Email-mediated Ad Hoc group of advisory to review and rank prior to Spring or Fall Advisory meeting |
| INSTRUCTIONAL QUALITY & EFFECTIVENESS Goal(s): |  |  |  |
| Identify and develop Web Programming Certificate of Proficiency outcomes and assessments | A draft of outcomes and assessments for Web Programming will be developed by Bob Hughes and Mark Smith and distributed to advisory for feedback | Spring 2011 Fall 2011 | Ad Hoc assignment to advisory feedback prior to Assessment committee approval |
| Identify and develop outcomes as a key component for the design of a new web/applications development program |  | Fall 2011 Winter 2012 | Ad Hoc assignment to advisory for approval Winter 2012 |

| INSTRUCTIONAL AND LEARNING EXPERIENCES Goal(s): |  |  |  |
| --- | --- | --- | --- |
| Identify outcomes of internal (class-based) learning, service-based learning projects, and external internship or incubator-based learning experiences that will enable students to have experiences preparing them for careers in web/applications development. or web support. | - Create a chart of the different types of learning experiences and environments integrated into the curricula with the end goal of a co-op or incubator experience - Get a list of new intern opportunities and possible long-term partners where students can gain work skills opportunities | Winter 2012 Spring 2012 | Email-mediated Ad Hoc group of advisory to review and develop prior to advisory in Winter or Spring when it is on the agenda |

| MARKETING/PUBLIC RELATIONS Goal(s): |  |  |  |
| --- | --- | --- | --- |
| Utilize a marketing model such a SIVA or 4Ps to help identify preliminary steps in identifying need and target audiences for a new web/applications development program. |  | Fall 2011 | Email-mediated Ad Hoc group of advisory for review and report prior to Fall 2011 Advisory meeting |